## Sheet1
Bug ID | Summary | Module | Severity | Steps to Reproduce | Expected Result | Actual Result | Status
BUG001 | Login button not working | Authentication | High | Click login after entering valid credentials | Redirect to homepage | Button unresponsive | Open
BUG002 | Product images not loading | Product Display | Medium | Open product details page | Product images displayed | Images not loading | Open
BUG003 | Cart quantity update issue | Cart Management | High | Update cart quantity | Quantity updated successfully | Quantity not updating | Open
BUG004 | Payment gateway timeout | Checkout | Critical | Attempt payment during checkout | Payment processed successfully | Payment gateway times out | Open
BUG005 | Order history not displaying | User Account | Medium | View order history | List of past orders displayed | No orders displayed | Open
BUG006 | Login session timeout too short | Authentication | Low | Stay inactive for a short period | Session remains active | Session times out too quickly | Open